## SL500EUUK
SL500EUUK Project Plan
Overall: 52% ¦ Start: 2026-03-03 ¦ MP Target: 2026-06-26 ¦ Duration: 113 days
No. | Task Name | Duration | Phase | Complete % | Status | Owner
7 | days
7 | days
7 | days
6 | days days,13
6 | days Factory
7 | days
7 | days
6 | days
7 | days
6 | days
7 | days
7 | days
7 | days Factory
7 | days Factory
7 | days Factory
6 | days Factory
6 | days Factory
6 | days CN Quality
7 | days Factory
7 | days
7 | days CN Testing
6 | days CN Testing
7 | days CN Testing,Factory
7 | days
7 | days Factory
1 | SL500UK&SL500EU Project Plan |  |  | 52% | In Progress
113 | days 26/3/3
1.1 | Kick Off Phase |  | Kick Off | 100% | Completed
4 | days
1.1.1 | Kick off |  | Kick Off | 100% | Completed
1 | day |  |  | 52% | In Progress
1.1.2 | Received PIS for EB1 |  | Kick Off | 100% | Completed
1 | day |  |  | 52% | In Progress
1.1.3 | Received UI Spec for EB1 |  | Kick Off | 100% | Completed
4 | days
1.1.4 | Received ID Spec EB1 |  | Kick Off | 100% | Completed
4 | days
1.2 | EB0 phase |  | EB0/Prototype | 61% | In Progress
95 | days 26/3/4
1.2.1 | Prepare product change PPT and ECN documents |  | EB0/Prototype | 100% | Completed
2 | days
1.2.2 | Finalize PSD and UI flow,confirm critical component |  | EB0/Prototype | 100% | Completed
2 | days
1.2.3 | Finalize sample plan for EB1 |  | EB0/Prototype | 100% | Completed
8 | days
1.2.4 | Provide redline EBOM |  | EB0/Prototype | 100% | Completed
8 | days
1.2.5 | Finalize CBOM for EB1 |  | EB0/Prototype | 100% | Completed
7 | days
1.2.6 | Approve ECN to DD |  | EB0/Prototype | 100% | Completed
15 | days
1.2.7 | PMO approve sample sample plan and release sample P.O to fatory |  | EB0/Prototype | 100% | Completed
4 | days
1.2.8 | Prepare UI mylar sample |  | EB0/Prototype | 100% | Completed
7 | days
1.2.9 | PCBA development for EB1 |  | EB0/Prototype | 0% | Not Started
52 | days
1.2.9.1 | Software development |  | EB0/Prototype | 100% | Completed
25 | days
1.2.9.1.1 | Send two samples to EE team (SL451UK) |  | EB0/Prototype | 100% | Completed
3 | days
1.2.9.1.2 | Finalize UI flow |  | EB0/Prototype | 0% | Not Started
1 | day |  |  | 52% | In Progress
1.2.9.1.3 | Software design |  | EB0/Prototype | 0% | Not Started
8 | days
1.2.9.1.4 | Reflash software |  | EB0/Prototype | 0% | Not Started
2 | days
1.2.9.2 | Delivery PCBA to factory |  | EB0/Prototype | 0% | Not Started
10 | days
1.2.9.3 | Performance test |  | EB0/Prototype | 0% | Not Started
3 | days
1.2.9.4 | NTK test |  | EB0/Prototype | 0% | Not Started
15 | days
1.2.10 | Color development |  | EB0/Prototype | 64% | In Progress
25 | days
1.2.10.1 | Send color chip to factory(Pantone 18-4214 TPG & |  | EB0/Prototype | 100% | Completed
4 | days
1.2.10.2 | Develop color 1st time |  | EB0/Prototype | 100% | Completed
7 | days
1.2.10.3 | CN CMF team review the 1st color (review result is negative) |  | EB0/Prototype | 100% | Completed
2 | days
1.2.10.4 | Develop 2nd color chips |  | EB0/Prototype | 0% | Not Started
7 | days
1.2.10.5 | CN-CMF team review the 2nd color sample |  | EB0/Prototype | 0% | Not Started
2 | days
1.2.10.6 | Approve color chips |  | EB0/Prototype | 0% | Not Started
2 | days
1.2.11 | Upload artwork for EB1 |  | EB0/Prototype | 0% | Not Started
1 | day |  |  | 52% | In Progress
1.2.12 | Prepare EB1 materials |  | EB0/Prototype | 0% | Not Started
12 | days
1.2.13 | EB1 assembly |  | EB0/Prototype | 0% | Not Started
6 | days
1.2.14 | Verfiy temperature and KPI data for EB1 samples |  | EB0/Prototype | 0% | Not Started
2 | days
1.2.15 | Conduct PSI + Calibration |  | EB0/Prototype | 0% | Not Started
2 | days
1.2.16 | Ship samples to US and UK team |  | EB0/Prototype | 0% | Not Started
5 | days
1.2.17 | Provide feedback of EB1 samples |  | EB0/Prototype | 0% | Not Started
5 | days
1.2.18 | Run EB1 DQTP |  | EB0/Prototype | 8% | In Progress
61 | days
1.2.18.1 | Conduct dishwasher test |  | EB0/Prototype | 100% | Completed
40 | days
1.2.18.2 | NTT test |  | EB0/Prototype | 0% | Not Started
7 | days
1.2.18.3 | Life test |  | EB0/Prototype | 0% | Not Started
30 | days
1.2.18.4 | Release DQTP report |  | EB0/Prototype | 0% | Not Started
1 | day |  |  | 52% | In Progress
1.2.18.5 | Run Food performance testing |  | EB0/Prototype | 0% | Not Started
24 | days
1.2.18.5.1 | Deliver samples to NTK team |  | EB0/Prototype | 0% | Not Started
2 | days
1.2.18.5.2 | Run KPI checkout |  | EB0/Prototype | 0% | Not Started
14 | days
1.2.18.6 | Run B/W testing |  | EB0/Prototype | 13% | In Progress
1.2.18.6.1 | Sent samples to EE teams |  | EB0/Prototype | 100% | Completed
1.2.18.6.2 | Arrange B/W testing |  | EB0/Prototype | 0% | Not Started
1.2.18.6.3 | Arrange UI flow check |  | EB0/Prototype | 0% | Not Started
24 | days
2 | days
14 | days
10 | days
1.2.19 | Run compliance testing |  | EB0/Prototype | 0% | Not Started
1.2.19.1 | Sent compliance samples to UL lab |  | EB0/Prototype | 0% | Not Started
1.2.19.2 | Conduct Compliance test |  | EB0/Prototype | 0% | Not Started
1.2.19.3 | Update compliance report& cert |  | EB0/Prototype | 0% | Not Started
1.3 | MP phase |  | DQTP/EB0 | 0% | Not Started
1.3.1 | Release LOA or PO for LLT material |  | DQTP/EB0 | 0% | Not Started
1.3.2 | Update ID & UI spec for MP |  | DQTP/EB0 | 0% | Not Started
1.3.3 | Upload artwork for MP |  | DQTP/EB0 | 0% | Not Started
1.3.4 | Approve digital proofs of AW |  | DQTP/EB0 | 0% | Not Started
1.3.5 | Update EBOM for MP |  | DQTP/EB0 | 0% | Not Started
1.3.6 | Update PCBA approval sheets |  | DQTP/EB0 | 0% | Not Started
1.3.7 | Update CBOM for MP |  | DQTP/EB0 | 0% | Not Started
1.3.8 | Prepare PKG for MP |  | DQTP/EB0 | 0% | Not Started
1.3.9 | Upload documents for ECN approval |  | DQTP/EB0 | 0% | Not Started
1.3.10 | Approve ECN |  | DQTP/EB0 | 0% | Not Started
1.3.11 | Release ECN to factory |  | DQTP/EB0 | 0% | Not Started
1.3.12 | Initiate MP Work Flow in PLM |  | DQTP/EB0 | 0% | Not Started
1.3.13 | Prepare MP materials |  | DQTP/EB0 | 0% | Not Started
1.3.14 | Sign golden samples for MP |  | DQTP/EB0 | 0% | Not Started
1.3.15 | Start MP |  | DQTP/EB0 | 0% | Not Started
33 | days
3 | days
20 | days
1 | day |  |  | 52% | In Progress
58 | days
1 | day |  |  | 52% | In Progress
5 | days
5 | days
2 | days
3 | days
5 | days
5 | days
12 | days
1 | day |  |  | 52% | In Progress
5 | days
1 | day |  |  | 52% | In Progress
5 | days
7 | days
1 | day |  |  | 52% | In Progress
1 | day |  |  | 52% | In Progress
7 | days
7 | days
7 | days
7 | days Factory
7 | days
7 | days Factory
7 | days Factory
7 | days Factory

## BW1001EUUK
BW1001EUUK Project Plan
Overall: 61% ¦ Start: 2025-12-15 ¦ MP Target: 2026-06-26 ¦ Duration: 194 days
No. | Task Name | Duration | Phase | Complete % | Status | Owner
1 | BW1001EUUK Project Plan |  |  | 61% | In Progress
194 | days
1.1 | Kick Off Phase |  | Kick Off | 100% | Completed
2 | days
1.1.1 | Kick Off |  | Kick Off | 100% | Completed
1 | day |  |  | 61% | In Progress
1.1.2 | Finalize PIS for EB0 |  | Kick Off | 100% | Completed
1 | day |  |  | 61% | In Progress
1.1.3 | Finalize UI Spec for EB0 |  | Kick Off | 100% | Completed
1 | day |  |  | 61% | In Progress
1.1.4 | Finalize ID Spec EB0 |  | Kick Off | 100% | Completed
1 | day |  |  | 61% | In Progress
1.2 | Prototype stage |  | EB0/Prototype | 100% | Completed
60 | days
1.2.1 | Prepare product change PPT and ECN documents |  | EB0/Prototype | 100% | Completed
2 | days
1.2.2 | DQTP & compliance Comment |  | EB0/Prototype | 100% | Completed
2 | days
1.2.3 | MIFA supplier selection |  | EB0/Prototype | 100% | Completed
3 | days
1.2.4 | Prepare sample for EMC & EPR & Structure | 12d | EB0/Prototype | 100% | Completed
1.2.5 | PCBA development for P1 |  | EB0/Prototype | 100% | Completed
43 | days
1.2.5.1 | PCBA hardware development |  | EB0/Prototype | 100% | Completed
40 | days
1.2.5.1.1 | Develop EMC devices,Microswitch | 15d | EB0/Prototype | 100% | Completed
1.2.5.1.2 | Prepare PCBA for EB0 |  | EB0/Prototype | 100% | Completed
13 | days
1.2.5.2 | Software development |  | EB0/Prototype | 100% | Completed
43 | days
1.2.5.2.1 | Make one unit sample with new PCBA |  | EB0/Prototype | 100% | Completed
6 | days
1.2.5.2.2 | Delivery unit sample to PCBA factory | 3d | EB0/Prototype | 100% | Completed
1.2.5.2.3 | Software design |  | EB0/Prototype | 100% | Completed
15 | days
1.2.5.2.4 | EMC test |  | EB0/Prototype | 100% | Completed
7 | days
1.2.6 | Delivery PCBA to factory |  | EB0/Prototype | 100% | Completed
3 | days
1.2.7 | Structure design for P1 |  | EB0/Prototype | 100% | Completed
21 | days
1.2.7.1 | Structure review |  | EB0/Prototype | 100% | Completed
3 | days
1.2.7.2 | Structure design |  | EB0/Prototype | 100% | Completed
11 | days
1.2.7.3 | ID Frozen(no change) |  | EB0/Prototype | 100% | Completed
14 | days
1.2.7.4 | Prototype material prepare |  | EB0/Prototype | 100% | Completed
7 | days
1.2.8 | Prototype Build & Test |  | EB0/Prototype | 100% | Completed
5 | days
1.2.9 | DQTP Test |  | EB0/Prototype | 100% | Completed
7 | days
1.2.10 | Kick off ECN and approve ECN to DD |  | EB0/Prototype | 100% | Completed
8 | days
1.3 | EB0 phase |  | DQTP/EB0 | 55% | In Progress
177 | days
1.3.1 | Finalize sample plan for EB0 |  | DQTP/EB0 | 0% | Not Started
10 | days
1.3.2 | Finalize EBOM and factory internal BOM for EB0 |  | DQTP/EB0 | 100% | Completed
6 | days
1.3.3 | Finalize CBOM for EB0 |  | DQTP/EB0 | 100% | Completed
6 | days
1.3.4 | PMO Release sample PO |  | DQTP/EB0 | 100% | Completed
7 | days
1.3.5 | Tooling manufacture |  | DQTP/EB0 | 6% | In Progress
87 | days
1.3.5.1 | Estimate tooling cost |  | DQTP/EB0 | 100% | Completed
5 | days
1.3.5.2 | Release tooling PO to factory |  | DQTP/EB0 | 100% | Completed
7 | days
1.3.5.3 | Tooling manufacture |  | DQTP/EB0 | 0% | Not Started
45 | days
1.3.5.4 | Mold trial and inject parts for EB0 |  | DQTP/EB0 | 0% | Not Started
4 | days
1.3.6 | Upload artwork for EB0 |  | DQTP/EB0 | 100% | Completed
5 | days
1.3.7 | Prepare EB0 materials |  | DQTP/EB0 | 0% | Not Started
25 | days
1.3.8 | Component level test for heating element |  | DQTP/EB0 | 0% | Not Started
40 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
6 | days
7 | days
7 | days
6 | days
2026 | Qtr 1
2026 | Qtr 2
2026 | Qtr 3
13 | days
7 | Prototype
1.3.9 | EB0 assembly |  | DQTP/EB0 | 100% | Completed
2 | days
1.3.10 | Verfiy temperature and KPI data for EB0 samples |  | DQTP/EB0 | 100% | Completed
2 | days
1.3.11 | Conduct PSI + Calibration |  | DQTP/EB0 | 100% | Completed
2 | days
1.3.12 | Ship samples to US and UK team |  | DQTP/EB0 | 100% | Completed
5 | days
1.3.13 | Provide feedback of EB0 samples |  | DQTP/EB0 | 100% | Completed
7 | days
1.3.14 | Run compliance testing |  | DQTP/EB0 | 8% | In Progress
74 | days
1.3.14.1 | Translated RL&IB Boilerplate |  | DQTP/EB0 | 100% | Completed
1 | day |  |  | 61% | In Progress
1.3.14.2 | Sample check and send to compliance | 3d | DQTP/EB0 | 100% | Completed
1.3.14.3 | Compliance test |  | DQTP/EB0 | 0% | Not Started
30 | days
1.3.14.4 | chemical test |  | DQTP/EB0 | 0% | Not Started
25 | days
1.3.14.5 | Get CB Report |  | DQTP/EB0 | 0% | Not Started
4 | days
1.3.15 | Run EB0 DQTP |  | DQTP/EB0 | 7% | In Progress
35 | days
1.3.15.1 | Conduct unit checkout |  | DQTP/EB0 | 100% | Completed
1 | day |  |  | 61% | In Progress
1.3.15.2 | Conduct Performance Test |  | DQTP/EB0 | 0% | Not Started
3 | days
1.3.15.3 | Conduct Reliability Life Test |  | DQTP/EB0 | 0% | Not Started
15 | days
1.3.15.4 | Conduct Safety Test |  | DQTP/EB0 | 0% | Not Started
12 | days
1.3.15.5 | Conduct Packaging Test |  | DQTP/EB0 | 0% | Not Started
2 | days
1.3.15.6 | Conduct PCBA level testing |  | DQTP/EB0 | 0% | Not Started
1 | day |  |  | 61% | In Progress
15 | days
1.3.15.8 | Release DQTP report |  | DQTP/EB0 | 0% | Not Started
2 | days
1.3.15.9 | Run Food performance testing |  | DQTP/EB0 | 0% | Not Started
35 | days
1.3.15.9.1 | Deliver samples to NTK team |  | DQTP/EB0 | 0% | Not Started
2 | days
1.3.15.9.2 | Run KPI checkout |  | DQTP/EB0 | 0% | Not Started
24 | days
1.3.16 | Run EE testing |  | DQTP/EB0 | 2% | In Progress
21 | days
1.3.16.1 | Deliver samples for DVT testing |  | DQTP/EB0 | 100% | Completed
2 | days
1.3.16.2 | Run BB testing |  | DQTP/EB0 | 0% | Not Started
14 | days
1.3.16.3 | Run WB testing |  | DQTP/EB0 | 0% | Not Started
14 | days
1.4 | MP phase |  | MP | 0% | Not Started
57 | days
1.4.1 | Release LOA or PO for LLT material |  | MP
1 | day |  |  | 61% | In Progress
1.4.2 | Update ID & UI spec for MP |  | MP
5 | days
1.4.3 | Upload artwork for MP |  | MP
1 | day |  |  | 61% | In Progress
1.4.4 | Approve digital proofs of AW |  | MP
2 | days
1.4.5 | Update EBOM for MP |  | MP
3 | days
1.4.6 | Update PCBA approval sheets |  | MP
5 | days
1.4.7 | Update CBOM for MP |  | MP
5 | days
1.4.8 | Prepare PKG for MP |  | MP
12 | days
1.4.9 | Upload documents for ECN approval |  | MP
1 | day |  |  | 61% | In Progress
1.4.10 | Approve ECN |  | MP
4 | days
1.4.11 | Release ECN to factory |  | MP
1 | day |  |  | 61% | In Progress
1.4.12 | Initiate MP Work Flow in PLM |  | MP
5 | days
1.4.13 | Prepare MP materials |  | MP
4 | days
1.4.14 | Sign golden samples for MP |  | MP
1 | day |  |  | 61% | In Progress
1.4.15 | Start MP |  | MP
1 | day |  |  | 61% | In Progress
6 | days
6 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
6 | days
7 | days
7 | days
7 | days
6 | days
7 | days
6 | days
7 | days
7 | days
7 | days
7 | days days
2026 | Qtr 1
2026 | Qtr 2
2026 | Qtr 3

## AS080UK&EU
AS080UK&EU Project Plan
Overall: 5% ¦ Start: 2026-03-23 ¦ MP Target: 2026-06-17 ¦ Duration: 85 days
No. | Task Name | Duration | Phase | Complete % | Status | Owner
1 | AS080UK/EU Project Plan |  |  | 5% | In Progress
85 | days
1.1 | Kick Off Phase |  | Kick Off | 69% | In Progress
5 | days
1.1.1 | Kick Off |  | Kick Off | 100% | Completed
1 | day |  |  | 5% | In Progress
1.1.2 | Finalize PIS for EB0 |  | Kick Off | 0% | Not Started
4 | days
1.1.3 | Finalize ID Spec EB0 |  | Kick Off | 0% | Not Started
4 | days
1.1.4 | Finalize UI Spec for EB0 |  | Kick Off | 0% | Not Started
4 | days
1.2 | EB1 phase |  | EB0/Prototype | 0% | Not Started
50 | days
1.2.1 | Prepare product change PPT and ECN documents |  | EB0/Prototype
1 | day |  |  | 5% | In Progress
1.2.2 | Create ECN |  | EB0/Prototype
1 | day |  |  | 5% | In Progress
1.2.3 | Prepare ECN DD documents (EE change PPT, Extensional SKU PPT, redline EBOM, | 4d | EB0/Prototype
1.2.4 | Finalize CBOM for EB0, provide unit cost to PMO |  | EB0/Prototype
5 | days
1.2.5 | Finalize sample plan for EB0 |  | EB0/Prototype
3 | days
1.2.6 | Sign off ECN to DD approved |  | EB0/Prototype
3 | days
1.2.7 | PMO approve sample sample plan and release P.O to fatory |  | EB0/Prototype
2 | days
1.2.8 | Prepare common parts for EB1 |  | EB0/Prototype
15 | days
1.2.9 | Packaging |  | EB0/Prototype
37 | days
1.2.9.1 | Freeze PIS |  | EB0/Prototype
0 | days
1.2.9.2 | Finish pulp tray CAD |  | EB0/Prototype
5 | days
1.2.9.3 | Make pulp tray prototype |  | EB0/Prototype
5 | days
1.2.9.4 | Generate tool plan for pulp tray tool |  | EB0/Prototype
4 | days
1.2.9.5 | Review pulp tray prototype and confirm it |  | EB0/Prototype
2 | days
1.2.9.6 | Approve tool cost and release pulp tray EPS tooling |  | EB0/Prototype
5 | days
1.2.9.7 | Release Tooling PO |  | EB0/Prototype
7 | days
1.2.9.8 | Fabricate pulp tray tooling |  | EB0/Prototype
20 | days
1.2.9.9 | Prepare pulp tray for EB1 |  | EB0/Prototype
2 | days
1.2.9.10 | Deliver pulp tray to facotory |  | EB0/Prototype
2 | days
1.2.10 | PCBA Software development |  | EB0/Prototype
34 | days
1.2.10.1 | Release and freeze UI flow and control flow for EB1 |  | EB0/Prototype
1 | day |  |  | 5% | In Progress
1.2.10.2 | Software design |  | EB0/Prototype
15 | days
1.2.10.3 | Delivery EB1 PCBA to factory |  | EB0/Prototype
1 | day |  |  | 5% | In Progress
1.2.11 | Color chip develop |  | EB0/Prototype
34 | days
1.2.12 | Upload artwork for EB1 (If necessary) |  | EB0/Prototype
1 | day |  |  | 5% | In Progress
1.2.13 | EB1 assembly |  | EB0/Prototype
2 | days
1.2.14 | Conduct PSI + Calibration |  | EB0/Prototype
2 | days
1.2.15 | Ship samples to US and UK team |  | EB0/Prototype
5 | days
1.2.16 | Provide feedback of EB1 samples |  | EB0/Prototype
2 | days
1.3 | Run EB1 DQTP |  | DQTP/EB0 | 0% | Not Started
32 | days
1.3.1 | Run unit check out |  | DQTP/EB0
1 | day |  |  | 5% | In Progress
1.3.2 | Run NTT test and bypass test |  | DQTP/EB0
7 | days
1.3.3 | Run life test |  | DQTP/EB0
30 | days
1.3.4 | Compression/vibration and drop test |  | DQTP/EB0
5 | days
1.3.5 | Environment test |  | DQTP/EB0
10 | days
1.3.6 | PCBA level test(if need) |  | DQTP/EB0
10 | days
1.3.7 | ABR test(if need) |  | DQTP/EB0
28 | days
1.3.8 | Release DQTP report |  | DQTP/EB0
1 | day |  |  | 5% | In Progress
1.4 | Compliance test |  | MP | 0% | Not Started
36 | days
1.5 | MP phase |  | MP | 0% | Not Started
58 | days
1.5.1 | Release LOA or PO for LLT material |  | MP
1 | day |  |  | 5% | In Progress
1.5.2 | Update ID & UI spec for MP |  | MP
1 | day |  |  | 5% | In Progress
1.5.3 | Approve artwork for MP |  | MP
15 | days
1.5.3.1 | Upload artwork for MP |  | MP
2 | days
1.5.3.2 | Provide digital proofs of MP AW |  | MP
2 | days
1.5.3.3 | Approve digital proofs |  | MP
2 | days
1.5.3.4 | Print PKG and collaterals for approval |  | MP
5 | days
1.5.3.5 | Approve printed PKG and collaterals on-site |  | MP
2 | days
1.5.4 | Update EBOM for MP |  | MP
3 | days
1.5.5 | Update CBOM for MP |  | MP
5 | days
1.5.6 | Update PCBA approval sheets |  | MP
5 | days
1.5.7 | Upload documents for ECN approval |  | MP
1 | day |  |  | 5% | In Progress
1.5.8 | Approve ECN to IMP |  | MP
1 | day |  |  | 5% | In Progress
1.5.9 | Release ECN to factory |  | MP
1 | day |  |  | 5% | In Progress
1.5.10 | Initiate MP Work Flow in PLM |  | MP
3 | days
1.5.11 | Prepare MP materials |  | MP
3 | days
1.5.12 | Sign golden samples for MP |  | MP
1 | day |  |  | 5% | In Progress
1.5.13 | Start MP |  | MP
1 | day |  |  | 5% | In Progress
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
6 | days
7 | days
7 | days
6 | days
6 | days
7 | days
6 | days
6 | days
6 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days days,64SS-25

## AS101KRxx
AS101KRxx Project Plan
Overall: 9% ¦ Start: 2026-03-18 ¦ MP Target: 2026-09-19 ¦ Duration: 183 days
No. | Task Name | Duration | Phase | Complete % | Status | Owner
1 | AS101KRxx Project Plan |  |  | 9% | In Progress
183 | days
1.1 | Kick Off Phase |  | Kick Off | 100% | Completed
3 | days
1.1.1 | Kick Off |  | Kick Off | 100% | Completed
1 | day |  |  | 9% | In Progress
1.1.2 | Provide PIS |  | Kick Off | 100% | Completed
1 | day |  |  | 9% | In Progress
1.1.3 | Finalize ID Spec for EB1 |  | Kick Off | 100% | Completed
3 | days
1.1.4 | Finalize UI Spec for EB1 |  | Kick Off | 100% | Completed
3 | days
1.2 | EB1 phase |  | EB0/Prototype | 12% | In Progress
149 | days
1.2.1 | Finalize PSD and UI flow,confirm critical component |  | EB0/Prototype | 99% | In Progress
13 | days
1.2.1.1 | Prepare product change PPT and ECN documents |  | EB0/Prototype | 100% | Completed
3 | days
1.2.1.2 | Prepare heating element samples for 220V/2000W |  | EB0/Prototype | 100% | Completed
12 | days
1.2.1.3 | Prepare motor samples for 220V/60HZ |  | EB0/Prototype | 100% | Completed
12 | days
1.2.1.4 | EE Change PPT |  | EB0/Prototype | 100% | Completed
4 | days
1.2.1.5 | P1 prototype Build |  | EB0/Prototype | 100% | Completed
3 | days
1.2.2 | Finalize sample plan for EB1 |  | EB0/Prototype | 0% | Not Started
5 | days
1.2.3 | Update redline EBOM for EB1 |  | EB0/Prototype | 0% | Not Started
3 | days
1.2.4 | Finalize CBOM for EB1 |  | EB0/Prototype | 0% | Not Started
3 | days
1.2.5 | Release Artwork for EB1 |  | EB0/Prototype | 0% | Not Started
5 | days
1.2.6 | PMO approve sample sample plan and release sample P.O to factory |  | EB0/Prototype | 0% | Not Started
4 | days
1.2.7 | Approve ECN to DD |  | EB0/Prototype | 0% | Not Started
10 | days
1.2.8 | Prepare materials for EB1 |  | EB0/Prototype | 0% | Not Started
15 | days
1.2.9 | PCBA development for EB1 |  | EB0/Prototype | 0% | Not Started
33 | days
1.2.9.1 | Software development |  | EB0/Prototype
21 | days
1.2.9.1.1 | Ship out retrofit unit to CN EE |  | EB0/Prototype
1 | day |  |  | 9% | In Progress
1.2.9.1.2 | Verfiy EMC test |  | EB0/Prototype
10 | days
1.2.9.1.3 | Update software for Korean |  | EB0/Prototype
15 | days
1.2.9.1.4 | Prepare PCBA for EB1(TBD) |  | EB0/Prototype
12 | days
1.2.10 | EB1 assembly |  | EB0/Prototype | 0% | Not Started
2 | days
1.2.11 | Verfiy temperature and KPI data for EB1 samples |  | EB0/Prototype | 0% | Not Started
2 | days
1.2.12 | Conduct PSI + Calibration |  | EB0/Prototype | 0% | Not Started
2 | days
1.2.13 | Ship samples to US and UK team |  | EB0/Prototype | 0% | Not Started
5 | days
1.2.14 | Provide feedback of EB1 samples |  | EB0/Prototype | 0% | Not Started
3 | days
1.2.15 | Get IHUT feedback for EB1 |  | EB0/Prototype | 0% | Not Started
64 | days
1.2.15.1 | Deliver IHUT smaples to users |  | EB0/Prototype
5 | days
1.2.15.2 | Get 1st week IHUT feedback |  | EB0/Prototype
20 | days
1.2.15.3 | Get 2nd week IHUT feedback |  | EB0/Prototype
5 | days
1.2.15.4 | Get 3rd week IHUT feedback |  | EB0/Prototype
5 | days
1.2.15.5 | Get 4th week IHUT feedback |  | EB0/Prototype
5 | days
1.2.15.6 | Get 5th week IHUT feedback |  | EB0/Prototype
5 | days
1.2.16 | Update compliance |  | EB0/Prototype | 0% | Not Started
94 | days
1.2.16.1 | Sent compliance samples (8pcs) |  | EB0/Prototype
2 | days
1.2.16.2 | Conduct Compliance test |  | EB0/Prototype
40 | days
1.2.16.3 | Get Korea Certification |  | EB0/Prototype
25 | days
1.2.17 | Run EB1 DQTP |  | EB0/Prototype | 0% | Not Started
38 | days
1.2.17.1 | Component level test for Motor and heating element |  | EB0/Prototype
30 | days
1.2.17.2 | Run unit check out |  | EB0/Prototype
2 | days
1.2.17.3 | Desktop temperature rise test |  | EB0/Prototype
5 | days
1.2.17.4 | Run life test |  | EB0/Prototype
30 | days
1.2.17.5 | Run NTT & Bypass test |  | EB0/Prototype
5 | days
1.2.17.6 | ABR test |  | EB0/Prototype
28 | days
1.2.17.7 | Release DQTP report |  | EB0/Prototype
1 | day |  |  | 9% | In Progress
1.2.18 | Run NTK testing |  | EB0/Prototype | 0% | Not Started
30 | days
1.2.18.1 | Deliver samples to NTK team |  | EB0/Prototype
2 | days
1.2.18.2 | Run KPI check out |  | EB0/Prototype
20 | days
1.2.19 | Run EE testing |  | EB0/Prototype | 0% | Not Started
23 | days
1.2.19.1 | Deliver samples for DVT testing |  | EB0/Prototype
2 | days
1.2.19.2 | Run BB testing |  | EB0/Prototype
15 | days
1.2.19.3 | Run WB testing |  | EB0/Prototype
15 | days
1.2.20 | PCBA&SW testing |  | EB0/Prototype | 0% | Not Started
22 | days
1.2.20.1 | Deliver samples for DVT testing |  | EB0/Prototype
1 | day |  |  | 9% | In Progress
1.2.20.2 | PCBA level test |  | EB0/Prototype
15 | days
1.2.20.3 | SW Check out test |  | EB0/Prototype
15 | days
1.3 | EB2 phase(Optional ) |  | DQTP/EB0 | 0% | Not Started
56 | days
1.4 | MP phase |  | MP | 0% | Not Started
51 | days
1.4.1 | Update PCBA approval sheets |  | MP
5 | days
1.4.2 | Release LOA or PO for LLT material |  | MP
1 | day |  |  | 9% | In Progress
1.4.3 | Update ID & UI spec for MP |  | MP
1 | day |  |  | 9% | In Progress
1.4.4 | Upload artwork for MP |  | MP
1 | day |  |  | 9% | In Progress
1.4.5 | Approve digital proofs of AW |  | MP
2 | days
1.4.6 | Prepare PKG for MP |  | MP
10 | days
1.4.7 | Update EBOM |  | MP
3 | days
1.4.8 | Update CBOM |  | MP
5 | days
1.4.9 | Upload documents for ECN approval |  | MP
1 | day |  |  | 9% | In Progress
1.4.10 | Approve ECN |  | MP
5 | days
1.4.11 | Release ECN to factory |  | MP
1 | day |  |  | 9% | In Progress
1.4.12 | Initiate MP Work Flow in PLM |  | MP
6 | days
1.4.13 | Prepare MP materials |  | MP
7 | days
1.4.14 | Prepare the chemical test material（100pcs） |  | MP
7 | days
1.4.15 | PPMP Build |  | MP
1 | day |  |  | 9% | In Progress
1.4.16 | Conduct PSI by quality team |  | MP
2 | days
1.4.17 | Review PSl report and get shippment approval |  | MP
2 | days
7 | days
7 | days
7 | days
6 | days
6 | days
7 | days
7 | days
6 | days
7 | days
7 | days
7 | days
7 | days
6 | days
6 | days
6 | days
7 | days
7 | days
7 | days
7 | days
7 | days
7 | days
6 | days
7 | days
7 | days
7 | days
7 | days
7 | days
6 | days
7 | days
6 | days
7 | days
7 | days
7 | days
6 | days
6 | days
7 | days
6 | days
7 | days
5 | days
2 | days
1 | day |  |  | 9% | In Progress
1.4.18 | Sign golden samples for MP |  | MP
1.4.18.1 | send golden Sample |  | MP
1.4.18.2 | Approval Golden Sample |  | MP
1.4.19 | Start MP |  | MP
6 | days
6 | days
6 | days